National ICT Database of Liberia (NICTD)

Data Mining Phase — Cost Schedule & Data Team

Labour costed on the client pay ladder: base US$50/day at the lowest grade, rising US$50 per grade. Companion live workbook: NICTD-Cost-Schedule.xlsx (editable rates, days & headcount).

1. Pay grade ladder

| Grade | Daily rate | Roles at this grade |
| --- | --- | --- |
| G1 | $50 | Enumerator (field data collector) |
| G2 | $100 | Facility / KII collector · Data processing clerk |
| G3 | $150 | Field supervisor · Data quality analyst |
| G4 | $200 | County research lead · Database/CAPI engineer · GIS analyst |
| G5 | $250 | Sampling statistician · Data Team lead |
| G6 | $300 | Survey / Project Director |

2. Field team labour (by county)

Cost = headcount x paid days x grade rate. Paid days: enumerators & KII 20, supervisors 25, research leads 30.

| County | Enum. | KII | Superv. | Leads | County cost |
| --- | --- | --- | --- | --- | --- |
| Montserrado | 13 | 3 | 3 | 1 | $36,250 |
| Nimba | 9 | 3 | 2 | 1 | $28,500 |
| Bong | 9 | 3 | 2 | 1 | $28,500 |
| Lofa | 8 | 2 | 2 | 1 | $25,500 |
| Grand Bassa | 8 | 2 | 2 | 1 | $25,500 |
| Margibi | 8 | 2 | 2 | 1 | $25,500 |
| Maryland | 7 | 2 | 2 | 1 | $24,500 |
| Grand Cape Mount | 7 | 2 | 2 | 1 | $24,500 |
| Grand Gedeh | 7 | 2 | 2 | 1 | $24,500 |
| Sinoe | 7 | 2 | 2 | 1 | $24,500 |
| Bomi | 7 | 2 | 2 | 1 | $24,500 |
| Gbarpolu | 7 | 2 | 2 | 1 | $24,500 |
| River Cess | 7 | 2 | 2 | 1 | $24,500 |
| River Gee | 7 | 2 | 2 | 1 | $24,500 |
| Grand Kru | 7 | 2 | 2 | 1 | $24,500 |
| FIELD TEAM TOTAL | 118 | 33 | 31 | 15 | $390,250 |

3. Data Team — post-collection processing (NEW)

A dedicated central team that turns raw field data into published NICTD indicators: cleaning, validation, weighting, coding, geocoding, database engineering and the bulk upload into the platform's review queue.

| Role | Responsibility | Grade | No. | Days | Cost |
| --- | --- | --- | --- | --- | --- |
| Data Team Lead | Owns the processing pipeline, review queue & final sign-off | G5 | 1 | 45 | $11,250 |
| Sampling Statistician | Weighting, county estimates, precision & error checks | G5 | 1 | 25 | $6,250 |
| Database / CAPI Engineer | Builds CAPI instrument, sync server, upload pipeline to NICTD | G4 | 2 | 30 | $12,000 |
| GIS / Mapping Analyst | Enumeration-area frames, geocoding, choropleth prep | G4 | 1 | 20 | $4,000 |
| Data Quality Analyst | Validation rules, cleaning, outlier & consistency review | G3 | 4 | 25 | $15,000 |
| Data Processing Clerk | Coding open responses, data entry backup, reconciliation | G2 | 6 | 15 | $9,000 |
| DATA TEAM TOTAL |  |  | 15 |  | $57,500 |

Workflow: field CAPI data -> nightly sync -> Data Quality Analysts clean & de-duplicate -> Statistician weights and computes county estimates -> GIS analyst maps -> Database/CAPI engineer formats to the platform CSV (indicator_code, county, year, value, source) -> Data Team Lead uploads via the Content Studio, passing automated validation and the human review queue -> live on NICTD.

4. Cost summary

| Cost component | Basis | USD |
| --- | --- | --- |
| Field team labour | 118 enumerators, 33 KII, 31 supervisors, 15 leads | $390,250 |
| Data team labour | 15-person central processing team | $57,500 |
| Central management | Survey/Project Director, G6, 55 days | $16,500 |
| Labour subtotal | field + data team + management | $464,250 |
| Contingency (10%) | editable in the workbook | $46,425 |
| Non-labour (optional) | transport, tablets, per-diem, training — fill if applicable | $0 |
| GRAND TOTAL | labour subtotal + contingency + non-labour | $510,675 |

5. Workforce recap

| Group | Headcount |
| --- | --- |
| Field data collectors (enumerators) | 118 |
| Facility / KII collectors | 33 |
| Field supervisors | 31 |
| County research leads | 15 |
| Data team (central) | 15 |
| Project director | 1 |
| TOTAL WORKFORCE | 213 |

Assumptions (all editable in NICTD-Cost-Schedule.xlsx): base rate $50 and $50 step; paid days per role as above; 10% contingency; non-labour set to $0 by default. Change the base rate, step, days or headcount in the blue cells and every total recalculates.