## Cost Summary
NICTD Data Mining Phase — Cost Summary
Live totals. Every figure here is a formula pulling from the other sheets — edit any blue input anywhere and this page updates instantly.
Cost component | Notes | USD
Field team labour | 118 enumerators, 33 KII, 31 supervisors, 15 leads (all 15 counties) | 390250
Data team labour | Post-collection processing (see Data Team sheet) | 57500
Central management | Survey/Project Director (G6) x 55 days | 16500
Labour subtotal | Field + Data Team + Management | 464250
Contingency | Editable % of labour subtotal -> | 46425 | 10%
Non-labour (optional) | Transport, tablets, per-diem, training — fill if applicable | 0
GRAND TOTAL | Labour subtotal + contingency + non-labour | 510675
Workforce recap
Group |  | Headcount
Total field workforce |  | 197
Data team headcount |  | 15
Grand total workforce |  | 213

## Pay Grades
Pay Grade Ladder
Only the two blue cells are inputs. Each grade = previous grade + step, so changing the base or the step recomputes every rate — and every cost on the other sheets.
Base daily rate (Grade 1, USD) | 50
Step per grade (USD) | 50
Grade | Daily rate (USD) | Example roles at this grade
G1 | 50 | Enumerator (field data collector)
G2 | 100 | Facility / KII collector · Data processing clerk
G3 | 150 | Field supervisor · Data quality analyst
G4 | 200 | County research lead · Database/CAPI engineer · GIS analyst
G5 | 250 | Sampling statistician · Data Team lead
G6 | 300 | Survey / Project Director

## Field Team Cost
Field Team Cost by County
Cost = headcount x paid days x grade rate. Edit any headcount (cols B-E) or the paid-days block (blue) and the county cost + totals recompute.
County | Enum. (n) | KII (n) | Superv. (n) | Leads (n) | County labour cost (USD) | Role | Paid days | Grade
Montserrado | 13 | 3 | 3 | 1 | 36250 | Enumerator | 20 | G1
Nimba | 9 | 3 | 2 | 1 | 28500 | Facility / KII collector | 20 | G2
Bong | 9 | 3 | 2 | 1 | 28500 | Field supervisor | 25 | G3
Lofa | 8 | 2 | 2 | 1 | 25500 | County research lead | 30 | G4
Grand Bassa | 8 | 2 | 2 | 1 | 25500
Margibi | 8 | 2 | 2 | 1 | 25500
Maryland | 7 | 2 | 2 | 1 | 24500
Grand Cape Mount | 7 | 2 | 2 | 1 | 24500
Grand Gedeh | 7 | 2 | 2 | 1 | 24500
Sinoe | 7 | 2 | 2 | 1 | 24500
Bomi | 7 | 2 | 2 | 1 | 24500
Gbarpolu | 7 | 2 | 2 | 1 | 24500
River Cess | 7 | 2 | 2 | 1 | 24500
River Gee | 7 | 2 | 2 | 1 | 24500
Grand Kru | 7 | 2 | 2 | 1 | 24500
FIELD TEAM TOTAL | 118 | 33 | 31 | 15 | 390250

## Data Team
Data Team — Post-Collection Processing
Central team that cleans, validates, weights, codes, maps and uploads the field data into NICTD. Edit headcount or paid days (blue) to recompute.
Role | Responsibility | Grade | Headcount | Paid days | Cost (USD)
Data Team Lead | Owns the processing pipeline, review queue & final sign-off | G5 | 1 | 45 | 11250
Sampling Statistician | Weighting, county estimates, precision & error checks | G5 | 1 | 25 | 6250
Database / CAPI Engineer | Builds CAPI instrument, sync server, upload pipeline to NICTD | G4 | 2 | 30 | 12000
GIS / Mapping Analyst | Enumeration-area frames, geocoding, choropleth prep | G4 | 1 | 20 | 4000
Data Quality Analyst | Validation rules, cleaning, outlier & consistency review | G3 | 4 | 25 | 15000
Data Processing Clerk | Coding open responses, data entry backup, reconciliation | G2 | 6 | 15 | 9000
DATA TEAM TOTAL |  |  | 15 |  | 57500