National ICT Database of Liberia (NICTD)

Data Mining Phase — Field Data Gathering Design & Survey Instruments

ICT Statistics & Policy Unit, Ministry of Posts & Telecommunications. Sampling and staffing computed from the 15-county population frame; see the companion workbook NICTD-Data-Mining-Phase.xlsx.

At a glance (all 15 counties)

| Metric | Value |
| --- | --- |
| Household interviews (completed / issued) | 9,980 / 11,360 |
| Enumeration areas (urban / rural) | 574 (170 / 404) |
| Field data collectors (enumerators) | 118 |
| Field supervisors | 31 |
| County research leads | 15 |
| Facility / key-informant collectors | 33 |
| Research cadre (leads + supervisors + KII) | 79 |
| Total field workforce | 197 |
| Duration (design to upload) | approx. 11 weeks |

The phase in 7 layers

Layer 0 — Source triage. Of 30 indicators, only 11 need the field: 7 via household survey, 2 via school visits, 2 via a price audit. The other 19 are operator feeds or desk/administrative requests.

Layer 1 — Sampling design. Two-stage stratified cluster sample; 20 households per enumeration area; Cochran n0 approx 384 (95%, +/-5%) with finite-population correction, design effect 1.5 and 12% non-response inflation. Completed interviews range 570 (smallest counties) to 1,160 (Montserrado).

Layer 2 — Field teams. Enumerators = completed / (6 per day x 15 days); 1 supervisor per 5 enumerators; 1 county research lead; 2-3 facility/KII collectors. 118 enumerators + 79 research cadre = 197 field staff.

Layer 3 — Geography & logistics. Urban and rural EAs per county proportional to urban share; teams based at county capitals; 4x4 access + travel days for the remote south-east and north-west; CAPI tablets with offline GPS-stamped capture.

Layer 4 — Timeline. Counties run in parallel: 2 wk design, 2 wk instruments, 1 wk training, 3-day pilot, 3 wk fieldwork, 2 wk cleaning, 1 wk analysis + upload = approx. 11 weeks.

Layer 5 — Instruments. Household ICT questionnaire (6 modules), school facility checklist, and tariff price sheet. Full household instrument below.

Layer 6 — Field to platform. CAPI capture to weighting to county estimates to the bulk-upload CSV (indicator_code, county, year, value, source) to Content Studio to validation to review queue to live publish.

County sampling & field-team plan

| County | Pop. | Urban | Completed | Issued | EAs | Enum. | Sup. | Lead | KII | Team |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Montserrado | 1761k | 85% | 1160 | 1310 | 66 | 13 | 3 | 1 | 3 | 20 |
| Nimba | 621k | 24% | 810 | 920 | 46 | 9 | 2 | 1 | 3 | 15 |
| Bong | 470k | 28% | 810 | 920 | 46 | 9 | 2 | 1 | 3 | 15 |
| Lofa | 397k | 20% | 690 | 790 | 40 | 8 | 2 | 1 | 2 | 13 |
| Grand Bassa | 288k | 32% | 690 | 790 | 40 | 8 | 2 | 1 | 2 | 13 |
| Margibi | 280k | 45% | 690 | 790 | 40 | 8 | 2 | 1 | 2 | 13 |
| Maryland | 173k | 28% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Grand Cape Mount | 165k | 18% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Grand Gedeh | 156k | 25% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Sinoe | 125k | 14% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Bomi | 110k | 30% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Gbarpolu | 100k | 12% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| River Cess | 96k | 8% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| River Gee | 89k | 10% | 570 | 650 | 33 | 7 | 2 | 1 | 2 | 12 |
| Grand Kru | 78k | 10% | 570 | 640 | 32 | 7 | 2 | 1 | 2 | 12 |
| NATIONAL | 4909k | - | 9980 | 11360 | 574 | 118 | 31 | 15 | 33 | 197 |

NICTD Household ICT Survey — Field Questionnaire

CAPI instrument (tablet). Codes in [brackets] are stored values. Every question carries a "Don't know" [98] and "Refused" [99] option. One questionnaire per sampled household; Module D/E individual questions are asked of one randomly selected adult (18+), with E1 asked of one adult man and one adult woman where present.

Module A — Identification & Consent

A1. County / District / Enumeration Area

[auto from sample frame]

A2. GPS coordinates

[auto-captured]

A3. Setting

Urban [1]   Rural [2]

A4. Read consent script. Does the respondent agree to participate?

Yes [1] -> continue   No [2] -> end & replace household

Consent script: voluntary, anonymous, aggregate statistics only, ~20 minutes, may stop anytime.

A5. Interviewer ID / Date / Start time

[auto]

Module B — Household Roster

B1. How many people usually live in this household?

[number]

B2. List each member: first name, age (years), sex (M[1]/F[2]), highest education completed.

[roster grid, one row per member]

Roster drives age/sex weighting and identifies eligible adults (18+) and youth (15-24).

B3. Randomly select ONE adult (18+) for the individual modules.

[CAPI auto-selects via Kish grid]

Module C — Household ICT Assets

C1. Does anyone in this household own a working mobile phone?

Yes [1]   No [2] -> skip to C3

C2. Is at least one of those phones a smartphone (can connect to the internet)?

Yes [1]   No [2]

Produces: smartphone_ownership (share of adults; combined with roster).

C3. Does this household have any of the following at home?

Radio [a]   Television [b]   Computer/laptop/tablet [c]   Fixed internet connection [d]   None [e]

C4. What is the household's main source of electricity?

Grid [1]   Generator [2]   Solar [3]   None [4]

Module D — Individual Internet Use  (randomly selected adult)

D1. Have you personally used the internet in the last 3 months, from any device or location?

Yes [1]   No [2] -> skip to D5   Don't know [98]

Produces: internet_penetration, and — split by A3 setting — urban_connectivity / rural_connectivity.

D2. Where do you usually access the internet?

Home [a]   Mobile data anywhere [b]   Work [c]   School [d]   Public Wi-Fi [e]   Cyber cafe [f]

D3. How often do you use it?

Daily [1]   At least weekly [2]   At least monthly [3]   Less than monthly [4]

D4. What do you mainly use it for?

Calls/messaging [a]   Social media [b]   News/info [c]   Education [d]   Work/business [e]   Government services [f]   Money/payments [g]

D5. If not / rarely: what is the main barrier?

Too expensive [1]   No network [2]   No device [3]   No skills [4]   Not interested [5]   Safety concerns [6]

Module E — Gender & Youth Module

E1. Ask ONE adult man and ONE adult woman in the household: Do you personally use the internet?

Man: Yes[1]/No[2]   Woman: Yes[1]/No[2]

Produces: gender_access_gap (male use rate minus female use rate, in percentage points).

E2. For each household member aged 15-24: Have you used the internet in the last 3 months?

Yes [1]   No [2]   per youth member

Produces: youth_access (internet use among 15-24 year-olds).

Module F — Affordability & Income

F1. In a usual month, about how much does this household spend on mobile airtime and data together?

[amount LRD or USD]   None [0]

F2. In a usual month, about how much on any fixed home internet?

[amount]   None [0]

F3. Which band best describes this household's total monthly income?

Lowest 20% [1]   2nd [2]   Middle [3]   4th [4]   Highest 20% [5]   Refused [99]

Produces: low_income_access (internet-use rate within band [1]); F1/F2 feed the affordability baskets alongside GNI per capita.

F4. Record end time. Thank the respondent.

[auto]

Companion Instruments

School Facility Checklist (Key-Informant)

Completed by a KII collector at each sampled school (EMIS frame). Produces school_connectivity and student_device_ratio.

S1. School name / EMIS code / county / setting

[from frame]

S2. Is there a working internet connection at the school today?

Yes [1]   Sometimes/unreliable [2]   No [3]

S3. Total enrolment (pupils)

[number]

S4. Number of internet-capable learning devices available to pupils

[number]

S5. Head-teacher: how is the connection used for teaching/administration?

[short text]

S6. Main barrier to connectivity

Cost [1]  No network [2]  No devices [3]  No power [4]  Other [5]

Tariff Price Sheet (Price Audit)

Completed in each county capital from each operator/ISP shop. Feeds mobile_basket_price and broadband_basket_price (with GNI per capita).

P1. Operator / ISP name

[text]

P2. Cheapest entry-level mobile bundle meeting the standard basket (data + voice), monthly price

[amount]

P3. Cheapest entry-level fixed-broadband plan, monthly price

[amount]

P4. Data allowance / speed of the quoted plans

[GB / Mbps]

P5. Date & location of price capture

[auto]